## Slide 1
Boerum Hill Town Hall
Brooklyn Dismantle
January 23, 2023
Borough-Based Jails

## Slide 2
1
March 5, 2020
Interim Sally Port and Dismantle Updates
Environmental Monitoring​
Community Engagement and Resources
Q&A
Agenda
2
3
4

## Slide 3
Interim Sally Port and Dismantle Updates
Brooklyn

## Slide 4: Project Schedule Milestones
Milestone | Estimated Dates
Site Assessment and Surveys (Verification of existing building conditions) | Complete
Mobilization / Site Fencing Site fencing, sidewalk shed installation, field office South Sidewalk Closure on State Street March 2022 (Pedestrian circulation will be maintained) | Complete
Interim Sally Port and Officer Booth Construction | April 2022 – January 2023
Dismantle Work - Oil Tank removal on the north side of State Street, remove and install new tanks (Winter 2022 – Summer 2023) -Temporary Sidewalk and Parking restrictions expected on Smith and State St. | January 2023– July 2023
Podium Dismantle - Removal of 1-2 story structure bordering Boerum Pl, Atlantic Ave., & Smith St. | October 2022 – January 2023
INFORMATIONAL PURPOSES ONLY
*Estimated Dates and Milestones will be updated by Design-Builder

## Slide 5: Overview of Dismantle Activities & Progress
Interim sally port and officer booth
Atlantic Ave
State St
Boerum Pl
Smith Street
Sidewalk Closure
Oil tank removal
Oil tank Installation
Podium dismantle progress
MTA Vent Shafts
Deliveries and Subcontractor Staging Area
Trailer
Offices
Trailer Offices
275 Atlantic Ave.
Prep site for tank excavation
Roof bulkhead & yard scaffolding
Hoist installation
Notes: DB Team

## Slide 6
Dismantle Progress Photos
Tower scaffolding around bulkhead and yard
1/13/23
Tower hoist construction
and operation
1/13/23
Completed
Officer Booth
1/13/23
Notes: DB Team

## Slide 7: Active Advisory Notice
Pedestrian Rerouting & No Placard Parking on State St. expected to start next Monday 1/23 through June 2023

## Slide 8
Environmental Monitoring
Brooklyn

## Slide 9
The BBJ team will provide quarterly environmental monitoring updates at Community Board and Neighborhood Advisory Committee (NAC) meetings.
The environmental monitoring reports and environmental factsheets are posted on the BBJ website: https://rikers.cityofnewyork.us/environmental-monitoring-reports/
Vibration Monitoring: (PSI Agency, Inc.)
Monitor 1 is placed within 120 Schermerhorn Street (Court Building).
Monitors are placed within the F train subway tunnel under Smith Street.
Baseline data collection was taken in April 2022.
Noise Monitoring: (PSI Agency, Inc.)
4 Monitors are at the sidewalk bridge locations at the center of Smith Street, Atlantic Avenue, Boerum Place, and State Street.
Noise monitoring is being performed on a continuous basis.
Air Quality Monitoring: (PSI Agency, Inc.)
4 particulate monitoring stations are at each corner of the site. Particulate monitoring is performed daily at 15-minute intervals.
The Action Level is set below the Permissible Exposure Levels (PEL) . When Action Levels are reached, the construction activities are assessed, and the contractor immediately acts to apply steps to control dust and emissions before the PEL is reached.
The BBJ Construction Management Team, Project Contractors and Environmental Specialists receive real time alerts when Particulate Matter (PM), decibels (dBa), or velocity of vibration (ips) number approach and Action Level.
Environmental Monitoring Updates
Vibration, Air and Noise monitoring devices installed by Design-Build team.
Atlantic Ave
State St
Boerum Pl
Smith Street
Notes: DB Team

## Slide 10
DECEMBER 2022 & JANUARY 2023 | NOVEMBER & DECEMBER 2022
Air Quality Monitoring | In December 2022 and January 2023, construction‐related levels of Particulate Matter (PM) PM10 did not surpass Daily Permissible Exposure Limits (PEL) as set by federal standards for the 24‐hour Time Weighted Average (TWA), or daily value, and did not cause air quality concerns to the public or on‐site workers.
Noise Monitoring | In December 2022 and January 2023, construction-related levels of noise did not surpass the limits of Local Law 113 and did not cause noise concerns for the community. No corrective actions or mitigation measures were required.
Vibration Monitoring | In December 2022 and January 2023 , no alarm was triggered during or by any construction activity. No corrective actions or mitigation measures were required.
Environmental Monitoring Updates
Monthly reports will be posted online: https://rikers.cityofnewyork.us/environmental-monitoring-reports/
*No exceedances are expected for the remainder of January. Levels will be continuously monitored, and corrective actions will be taken if necessary*
Notes: DB Team

## Slide 11
Community Engagement and Resources
Brooklyn

## Slide 12: Community Resources During Construction
BBJ Website
Designated Phone Number
Weekly Look Ahead
72-Hour Advisories for Impactful Construction Activities
Community Construction Liaison & Field Office
https://rikers.cityofnewyork.us/
Lucien Allen Brooklyn BBJ CCL
(917) 270-2370 / BrooklynCCL@bbjnyc.com
360 Atlantic Avenue
Monday – Friday 7:00am - 3:30pm

## Slide 13
Q & A
Brooklyn

## Slide 14
Thank You
Borough-Based Jails | NAC
Brooklyn Dismantle